## SUMMARY
SPARK UPDATE - March 2026
SUMMARY
| Package |  |  |  | TOTAL
| 1 | 2 | 3 | 4
Instructed via Work Order | 82 | 77 | 65 | 84 | 308
Works commenced | 30 | 22 | 15 | 15 | 82
Paving Works | 27 | 31 | 8 | 15 | 81
Works scheduled to commence end of March | 10 | 12 | 19 | 20 | 61
Works scheduled to commence in April | 3 | 12 | 10 | 18 | 43
Works scheduled to commence in May | 12 | 0 | 2 | 12 | 26
Works scheduled to commence in June | 0 | 0 | 6 | 4 | 10
Works scheduled to commence in July | 0 | 0 | 5 | 0 | 5
To be instructed via Work Order | 34 | 29 | 12 | 10 | 85
TOTAL | 116 | 106 | 77 | 94 | 393

## Package 1
Parishes | Road Corridor (Local & PC) | Estimate based on CHEC's Rates ($) | Status
St. Thomas | Phillips Field Road New Pera | 50000000 | Base works ongoing
| Curtis Bottom/ Cotton Tree Road | 52184433.35 | Drainage works ongoing
| Land Top Road | 45097654.95 | Drainage works ongoing
| Needham Pen Road | 40000000 | Scheduled to commence in May
| Mahagony Vale to Hagleys Gap | 50000000 | To be included in subsequent work order
| Ridge to White Hall | 50000000 | Scheduled to commence in April
| Wyatt to Seafort | 61005758.12 | Base works ongoing
| Poorman's Corner to Heartease | 50000000 | Scheduled to commence in April
| Albion Double Drive | 50000000 | Scheduled to commence in April
| Abilabi Lane | 50000000 | To be included in subsequent work order
Kingston Kingston | Campbell Street / Hampton Street | 11984680.18 | Drainage works ongoing
| Goodwin Park Road - Campbell Town | 17435771.51 | Pipeline works ongoing
| Woggonette Crescent - Kingston Garden | 14621097.31 | Scheduled to commence in March
| Mc Whinney Street | 9038774.02 | Pipeline works ongoing
| Albion Lane - Franklyn Town | 13184385.75 | Scheduled to commence in March
| Lincoln Terrace - Franklyn Town | 4977221.22 | Pavement works ongoing
| Seaforth Street run into Vincenth Street ( Allman Town) | 20000000 | Scheduled to commence in May
| Madison Avenue | 7500000 | Scheduled to commence in May
| Belview Avenue | 12639649.55 | Pavement works ongoing
| St. Georges | 15000000 | To be included in subsequent work order
| St. Patrick Roads | 15000000 | To be included in subsequent work order
| Everest Drive | 93209505.58 | Pavement works ongoing
| Balkan Drive | 51000000 | Drainage works ongoing
| Wareham Road | 7500000 | Scheduled to commence in March
| Bustamante Highway | 24, 194,255.38 | Pavement works ongoing
| Upper Church Street | 32677193.26 | Scheduled to commence in March
| Greenwich Street | 36032566.37 | Scheduled to commence in March
| Percy Street, from wellington Street to Regent | 14609818.04 | Drainage works ongoing
| Tulip Lane, from Last Street to Oxford Street | 5000000 | To be included in subsequent work order
| Percy Street, from Blount Street to Oxford Street | 14907134.53 | Drainage works ongoing
| Regent Street and Charles Street | 25000000 | To be included in subsequent work order
| Regent Street and North Street |  | To be included in subsequent work order
| Roase Lane and Charles Street |  | Scheduled to commence in May
| Love Lane above North Street | 35000000 | To be included in subsequent work order
| Hanna Street Sidewalk |  | To be included in subsequent work order
| Drummond Street, from Princess Street to Orange Street |  | Scheduled to commence in May
| New North Street, from Kings Street to Crab Ground | 9019412.87 | Pavement works ongoing
St. Andrew St. Andrew St. Andrew St. Andrew | Ebenezer Avenue, New Haven | 31000000 | To be included in subsequent work order
| Longfellow Avenue, Duhaney Park | 55757340.03 | Drainage works ongoing
| Mansfield Avenue, Washington Gardens | 23481426.09 | Pavement works ongoing
| Righton Crescent, Washington Gardens | 22162396.25 | Drainage works ongoing
| Portlawn Avenue, Riverton City | 15000000 | To be included in subsequent work order
| Trelawny Crescent, Riverton City | 15000000 | To be included in subsequent work order
| West Bayfarm Road | 100307578.05 | Scheduled to commence in March
| Dillpath Crescent | 15000000 | To be included in subsequent work order
| Wellside Crescent | 34000000 | To be included in subsequent work order
| Callaloo Mews (Spanish Town Road) | 12500000 | To be included in subsequent work order
| Manley Avenue | 25000000 | To be included in subsequent work order
| Tavern Drive | 50000000 | Scheduled to commence in May
| Tavern Crescent | 22995919.68 | Pavement works ongoing
| Blue Castle Terrace | 50000000 | To be included in subsequent work order
| Catus Way, Marigold Way and Iris Close | 25159977.54 | Pavement works ongoing
| East Pine Way & West Pine Way | 13930715.45 | Pavement works ongoing
| Doherty Drive | 27083408.15 | Pavement works ongoing
| Clieveden | 44730229.03 | Pavement works ongoing
| Providence Pen Lane | 10484281.77 | Scheduled to commence in March
| Swallowfield Road | 40000000 | Base works ongoing
| Watson Ave | 8750000 | Scheduled to commence in May
| Sackville Road | 26000000 | Scheduled to commence in May
| Vineyard Road | 39000000 | Scheduled to commence in May
| Antrim Road | 46500000 | Scheduled to commence in March
| Lexington Ave | 32500000 | To be included in subsequent work order
| Passion Gardens (Toby Gully) both left and right return off | 52628951.93 | Pavement works ongoing
| Middleton/Settlement | 82248512.94 | Pavement works ongoing
| Two Three to Jack Allen & turn off to Freetown | 82248512.94 | Scheduled to commence in March
| Hope Flats / Penny Gully | 60000000 | Scheduled to commence in May
| Bayview Retreat Drive | 30838210.68 | Pavement works ongoing
| Torrington Park | 8349944.88 | Pavement works ongoing
| Baker Street | 15000000 | To be included in subsequent work order
| Mulgrave Road | 8730350.88 | Base works ongoing
| Lincoln Road | 20000000 | To be included in subsequent work order
| Collie Smith Drive | 168618748.49 | Pavement works ongoing
| Lincoln Crescent (Block Roses) | 18008605.16 | Drainage works ongoing
| Avon Park Crescent | 15000000 | To be included in subsequent work order
| West Road (Top & Lower) | 25000000 | To be included in subsequent work order
| Golding Road | 15000000 | To be included in subsequent work order
| Grants Pen Drive | 31785299.49 | Drainage works ongoing
| Markland Avenue | 30240772.46 | Pavement works ongoing
| Shortwood Lane | 17500000 | To be included in subsequent work order
| Liguanea Avenue | 77630767.17 | Pavement works ongoing
| Waterloo Avenue | 32500000 | To be included in subsequent work order
| Surbiton Road | 21250000 | To be included in subsequent work order
| Annette Crescent | 30000000 | To be included in subsequent work order
| Richings Avenue | 18655181.09 | Pavement works ongoing
| Oakland Crescent | 39682825.75 | Drainage works ongoing
| Bartley Lane | 25000000 | Scheduled to commence in May
| Majesty Gardens Side Walk | 21086919.7 | Drainage works ongoing
| Brotherton Avenue (road,side walk) | 40000000 | To be included in subsequent work order
| Oakland Road | 52223435.71 | Drainage works ongoing
| Harvey Road | 12867245.05 | Pavement works ongoing
| Orange Grove Road | 15913950.41 | Completed
| Christopher Boulevard | 10000000 | To be considered in subsequent work order
| Karl Samuda Road | 15000000 | To be considered in subsequent work order
| Lady Huggin | 12500000 | To be considered in subsequent work order
| Park Lane | 20000000 | To be considered in subsequent work order
| 32 & 34 White Hall Avenue | 25000000 | To be considered in subsequent work order
| Upper Aries | 108563342.42 | Pavement works ongoing
| Ursa Minor | 45834155.02 | Completed
| Mount Charles - Luna | 40795623.26 | Scheduled to commence in March
| Blue Mountain | 51180132.54 | Pavement works ongoing
| Seaview Road | 110000000 | Drainage works ongoing
| Brooks Level Road | 48891818.74 | Drainage works ongoing
| Castle Drive | 50000000 | Scheduled to commence in May
| East Road | 92590121.49 | Pavement works ongoing
| Gentles Road | 22437574 | Drainage works ongoing
| Marverly Avenue | 47930090.29 | Drainage works ongoing
| Sundown Crescent | 80000000 | To be included in subsequent work order
| Central Road | 15000000 | To be included in subsequent work order
| Langard Road | 62560780.13 | Drainage works ongoing
| Randolph Avenue | 6000000 | To be included in subsequent work order
| Sutherland Avenue | 5500000 | To be included in subsequent work order
| Topaz Crescent | 41143304.52 | Drainage works ongoing
| Addington Drive | 24413457.57 | Pavement works ongoing
| Lower Turnbridge Drive | 25000000 | To be included in subsequent work order
| Greendale Crescent | 5000000 | Pavement works ongoing
| Patosi Ave. | 10000000 | To be included in subsequent work order
| Elma Crescent | 20000000 | To be included in subsequent work order
| Monterey Ave. | 44844753.1 | Base works ongoing
| Lockhart Ave. |  | Base works ongoing
| Woodpecker Avenue | 75000000 | Pipeline works ongoing
| Simon Taylor Road | 31500000 | Drainage works ongoing
| Henry Morgan Avenue | 14500000 | Base works ongoing

## Package 2
Parishes | Road Corridor (Local & PC) | Estimate based on CHEC's Rates ($) | Status
St. Catherine St. Catherine St. Catherine St. Catherine | New Mountain | 42500000 | To be included in subsequent Work Order
| Water Lane | 34104595.17 | Drainage works ongoing
| Martin Lane | 16000000 | To be included in subsequent Work Order
| Bullet Tree | 26070386.95 | Pavement works ongoing
| Bushy Park | 101367704.84 | Pipeline works ongoing
| Mahoe Drive - Bridgeview | 26905971.09 | Pavement works ongoing
| Susan Ave. - Edgewater | 64119903.55 | Pavement works ongoing
| Coral Way - West Bay | 20000000 | Scheduled to commence in March
| Autumn and Spring Crescent - Bridgeport | 20000000 | Scheduled to commence in April
| Westport | 35000000 | Scheduled to commence in April
| Levens Crescent - Cumberland | 25000000 | To be included in subsequent Work Order
| Middlesex Ave. - Independence City | 20000000 | Pavement works ongoing
| Henderson Drive - Independence City | 15000000 | To be included in subsequent Work Order
| Maryland - Waterford | 20000000 | To be included in subsequent Work Order
| Ramble Road - Waterford | 20000000 | To be included in subsequent Work Order
| Jones Avenue | 32908049.33 | Pavement works ongoing
| Gilgael Avenue | 20162931.99 | Scheduled to commence in March
| New Nursery | 29529222.61 | Pavement works ongoing
| Tredegar Park Road | 70000000 | To be included in subsequent Work Order
| Zambia Ave | 70000000 | To be included in subsequent Work Order
| Caymanas Gardens | 40000000 | Scheduled to commence in April
| Ransford Close | 11832582.23 | Pavement works ongoing
| Salah Close | 10000000 | Scheduled to commence in April
| Nova Close | 6000000 | Scheduled to commence in April
| Comit Close | 6000000 | Scheduled to commence in April
| Daisy Close | 5018324.99 | Pavement works ongoing
| Jasmine Close | 6499838.79 | Pavement works ongoing
| Queens Ave | 20000000 | Pavement works ongoing
| Dover Ave | 22500000 | Pavement works ongoing
| Walkers Ave | 15000000 | To be included in subsequent Work Order
| Lime Tree Crescent | 12500000 | To be included in subsequent Work Order
| Power Ave | 21854664.94 | Pavement works ongoing
| Myers Town | 20000000 | To be included in subsequent Work Order
| Facey | 22335339.8 | Pavement works ongoing
| Lodge (Top Mountain) | 45192040.72 | Pavement works ongoing
| Mountain Pass | 50934700.98 | Pavement works ongoing
| Coolshade (Goba) | 30588062.71 | Drainage works ongoing
| Meuse | 65000000 | To be included in subsequent Work Order
| Jubilee Town | 20000000 | To be included in subsequent Work Order
| Arlington Road | 97561597.72 | Pipeline works ongoing.
| Willowdene Drive | 44594245.65 | Pavement works ongoing
| Homestad Boulevard | 50769464.88 | Pavement works ongoing
| Cassino Drive | 20000000 | To be included in subsequent Work Order
| West Bank | 19859478.24 | Scheduled to commence in March
| First Street | 10000000 | To be included in subsequent Work Order
| First Ave | 20000000 | To be included in subsequent Work Order
| NE 15th Street 6E Greater Portmore | 9779174.99 | Pavement works ongoing
| NE 14th Street 6E Greater Portmore | 16657720.34 | Pavement works ongoing
| Port Royal Square | 7500000 | Scheduled to commence in April
| Cartagena Square | 7500000 | Scheduled to commence in April
| Hellshire Beach Main Rd | 5000000 | Scheduled to commence in April
| Sandhills Main Rd | 108534757.95 | Pavement works ongoing
| Manley Lane | 20000000 | To be included in subsequent Work Order
| Stella Wilkins Drive | 11000000 | To be included in subsequent Work Order
| West Prospect to Cashew Walk | 37802984.34 | Scheduled to commence in March
| South Monticello Crescent | 48605283.56 | To be included in subsequent Work Order
| Benneth Lane to Cedar Valley | 63554537.68 | Pavement works ongoing
| Buena Vista | 92980481.99 | Drainage works ongoing
| Brown's Town/Nugent Street | 96404337.93 | Scheduled to commence in March
| Tucker Road | 103261286.954 | Pipeline works ongoing
| York Street | 126347296.71 | Pavement works ongoing
| Mount Pleasant Road | 79275108.55 | Pipeline works ongoing
| Watermount to Bolas | 60973639.43 | Drainage works ongoing
| Friendship Drive | 121631061.67 | Pipeline works ongoing
| Gutter Mountain Rd | 78638600.45 | Scheduled to commence in March
| Prince Avenue | 25619657.04 | Base works ongoing
| Cumberland Road | 61709286.28 | Drainage works ongoing
| Williams Street | 78415916.1 | Drainage works ongoing
| Eltham Boulevard | 140786230.56 | Pavement works ongoing
| Anthurium | 35000000 | To be included in subsequent Work Order
| Ensom Avenue | 30000000 | To be included in subsequent Work Order
| Chensinton/Westmore | 55000000 | To be included in subsequent Work Order
| Irish Pen | 15000000 | To be included in subsequent Work Order
| North Drive/Hampton Avenue | 55000000 | To be included in subsequent Work Order
Clarendon Clarendon | Orange River | 70000000 | Scheduled to commence in April
| John's Hall | 110000000 | Scheduled to commence in March
| New Road | 40373315.89 | Drainage works ongoing
| Damn Road | 42530522 | Pavement works ongoing
| Mosquito Road | 24788745.32 | Pavement works ongoing
| Belmont Road | 51750042.52 | Scheduled to commence in March
| Orange Hill Road | 71459441.01 | Drainage works ongoing
| Morgans Road | 86496219.24 | Drainage works ongoing
| Top Alstan School Road | 112590470.26 | Drainage works ongoing
| Girls Town to White Road | 82051183.36 | Base works ongoing
| Bottom Halse Hall to Top Halse Hall | 55749414.63 | Pipeline works ongoing
| First Entrance of New Bowens to Hillview | 75153956.48 | Pavement works ongoing
| Joe Reid | 70000000 | To be included in subsequent Work Order
| Kennedy Drive | 50000000 | Scheduled to commence in March
| Top Hill to Waterlane | 50000000 | To be included in subsequent Work Order
| York Circle | 30999812.84 | Pavement works ongoing
| Gravel Hill Road | 66914830.88 | Drainage works ongoing
| Duke Dstreet | 40000000 | To be included in subsequent Work Order
| Havanna Heights Phase 3 | 65504833.93 | Pavement works ongoing
| Havanna Heights Phase 1 | 52118091.76 | Drainage works ongoing
| Cotton Ground | 41380544.1 | Scheduled to commence in March
| Post Road Bottom | 65000000 | Scheduled to commence in April
| Gold Ring Hill | 17421123.17 | Pavement works ongoing
| Colonels Ridge School Road | 35000000 | Scheduled to commence in April
| Stewarton | 61255840.52 | Pavement works ongoing
| Mount Valley | 34840355.62 | Pavement works ongoing
| Effortville to Long Gully | 32434305.71 | Scheduled to commence in March
| Bucknor (Bottom Road) | 65447153.08 | Drainage works ongoing
| Mud Lane (West Park) | 35000000 | To be included in subsequent Work Order
| Cemetry Road | 25000000 | To be included in subsequent Work Order
| Circle Drive | 25000000 | To be included in subsequent Work Order
| Inglewood Drive | 60959825.38 | Drainage works ongoing
| Wellington Drive | 21796157.69 | Scheduled to commence in March
| Woodleigh to Curatoe Hill | 25000000 | To be included in subsequent Work Order

## Package 3
Parishes | Road Corridor (Local & PC) | Estimate based on CHEC's Rates ($) | Status
Manchester | Wilbin - Heartease (Link road ) | 40070960.15 | Scheduled to commence in March
| Barnstaple | 52673702.98 | Pavement works ongoing
| Berrick Town | 67092876.86 | Base works ongoing
| Ingleside | 65000000 | Scheduled to commence in March
| Lincoln - Mt Prospect | 100000000 | Scheduled to commence in March
| George Reid | 35000000 | To be included in subsequent work order
| Beverly Green /Battersea | 52385988.79 | Base works ongoing
| Evergreen | 46102610.56 | Pavement works ongoing
| Wickwar - Silver Grove | 25000000 | To be included in subsequent work order
| Providence | 45000000 | Scheduled to commence in March
| Kingsland Sub Division Road | 25000000 | Scheduled to commence in June
| New Green | 60000000 | To be included in subsequent work order
| Haughton Pond Road | 83719126.47 | Drainage works ongoing
| Smithfield Road | 49912491.7 | Pavement works ongoing
| Little Portmore in Plowden | 26228896.31 | Scheduled to commence in March
| Ebenezer School Road | 75000000 | Scheduled to commence in March
| Top Road, Rose Hill | 25000000 | Scheduled to commence in March
| Ticky Ticky | 100000000 | To be included in subsequent work order
| Lyn's Avenue (NWC to review need for pipeline works) | 32360905.35 | Pavement works ongoing
| Jobs Lane/Othersfield/Savoy | 38686776.71 | Scheduled to commence in March
| Mckie Pipe House Road (NWC to review need for pipeline works) | 38409839.31 | Scheduled to commence in March
St. Elizabeth | Red Hills, Haughton | 55000000 | Scheduled to commence in April
| Holland Village (Playfield Rd & Middle Rd) | 83001947.78 | Pipeline works ongoing
| Grove Hill, White Hill | 36255618.36 | Drainage works ongoing
| Long Ground, New Market | 50000000 | Scheduled to commence in April
| Tryal | 50002294.68 | Pavement works ongoing
| Gayle Town | 28119407.6 | Pavement works ongoing
| Broomfield Town | 75000000 | Drainage works ongoing
| Queens Berry | 47294831.34 | Base works ongoing
| Slipe (Fullerswood Road to Slipe to Frenchman) | 141751803.59 | Pavement works ongoing
| School House to Ditingent (Middlequarters) | 78503243.5 | Pipeline works ongoing
| Pondside Road to Hiltop | 85000000 | Scheduled to commence in March
| Coffee Lane | 19518530.56 | Pipeline works ongoing
| Brighton | 46817260.46 | Pavement works ongoing
| Park Mountain (pass school upward) | 75000000 | Scheduled to commence in May
| New River | 50000000 | To be included in subsequent work order
| Rangle Lane | 45000000 | Scheduled to commence in May
| Burton Lane | 15000000 | To be included in subsequent work order
Westmoreland | Porters Mountain | 75000000 | To be included in subsequent work order
| Welcome to Maxfield | 30213621.47 | Base works ongoing
| Whithorn to Logwood | 26124409.5 | Base works ongoing
| Desta to Cooke Street | 20000000 | Scheduled to commence in June
| Segree Street | 30000000 | Scheduled to commence in July
| Farm Pen | 20000000 | Scheduled to commence in June
| Poppy Street | 25000000 | Scheduled to commence in July
| Board Walk Scheme | 20000000 | To be included in subsequent work order
| New Town | 25000000 | To be included in subsequent work order
| Gordon Road to Congress (Whitehouse Division) | 51585882.49 | Scheduled to commence in March
| Argyle Mountain to Castle Mountain Road (bethel Town Div.) | 48981859.07 | Scheduled to commence in March
| Orange Hill - Bottom Darliston (Darliston Division) | 40000000 | Scheduled to commence in April
| Lennox Bigwoods including McDonald Road (Darliston Div.) | 80000000 | Scheduled to commence in April
| Ashton to Leamington (Leamington Division) | 80000000 | Scheduled to commence in April
| Wild -Pine | 35000000 | To be included in subsequent work order
| Townhead | 30000000 | Scheduled to commence in March
| Blackness | 24216482.48 | Drainage works ongoing
| Geneva - Ghetto | 56594421 | Drainage works ongoing
| Crowder | 15000000 | Scheduled to commence in June
| Camp Savannah Mountain | 45000000 | Scheduled to commence in July
| Shanty Town | 25000000 | To be included in subsequent work order
| Revival | 25000000 | Scheduled to commence in March
| Villa La Cage | 25000000 | To be included in subsequent work order
Hanover | Hopewell - Chigwell | 71557700.82 | Scheduled to commence in April
| Success | 20000000 | Scheduled to commence in March
| Top Hill | 43696304.66 | Drainage works ongoing
| Zion - Cho cho Lane | 25000000 | Scheduled to commence in March
| Pondpiece- Sea Top | 25000000 | Scheduled to commence in March
| Claremont | 25000000 | Scheduled to commence in April
| 1 Central - Taylor Drive - Zion | 25000000 | Scheduled to commence in April
| Well Lane | 15000000 | Scheduled to commence in June
| Daffodil- Voilet | 30000000 | Scheduled to commence in March
| Malcolm Heights | 38487831.77 | Drainage works ongoing
| Riverside to Rugland | 64892754.53 | Scheduled to commence in March
| Blair Castle | 25000000 | Scheduled to commence in June
| Richmond to Cacoon | 65000000 | Scheduled to commence in April
| Prosper Road | 25000000 | Scheduled to commence in July
| Francis Town | 42500000 | Scheduled to commence in July
| Askenish to Clifton | 25000000 | Scheduled to commence in April

## Package 4
Parishes | Road Corridor (Local & PC) | Estimate based on CHEC's Rates ($) | Status
St. James St. James | Canaan-Dip | 22928816.81 | Scheduled to commence in March
| Williamsfield | 85000000 | Scheduled to commence in April
| Burnt Ground | 125000000 | Scheduled to commence in April
| Greenwood | 107140671.61 | Pipeline works ongoing
| Bottom Road, Cambridge | 25000000 | Scheduled to commence in May
| Richmond Hill to Mafoota | 25000000 | Scheduled to commence in June
| Brother's Retreat, Garlands | 25000000 | To be included in subsequent work order
| Horse Guard, Garlands | 69266267.22 | Scheduled to commence in March
| Catskin, Stonehenge | 25000000 | To be included in subsequent work order
| Maldon Road, Maroon Town | 25000000 | Scheduled to commence in March
| Brissett Road, Cambridge | 19203840.26 | Pipeline works ongoing
| School Road, Niagara | 25000000 | Scheduled to commence in April
| Old Jackson Road, Maroon Town | 25000000 | Scheduled to commence in April
| Comfort Hall to Walespond Road | 50000000 | Scheduled to commence in April
| Felman Corner | 15000000 | Scheduled to commence in April
| Flower Hill Main | 25000000 | Base works ongoing
| Unity Close | 25340999.53 | Base works ongoing
| Unity Crescent | 49539019.54 | Drainage works ongoing
| Unity Heights | 10000000 | To be included in subsequent work order
| Pop Lawrence Blvd | 15000000 | To be included in subsequent work order
| Lazaretta Drive | 20000000 | Scheduled to commence in April
| Bayroute Ring Road | 20000000 | Scheduled to commence in May
| Cornwall Gardens | 25000000 | Scheduled to commence in May
| Barbados to Caribbean Terrace | 25000000 | Scheduled to commence in June
| Kodac Street | 57287313.26 | Pavement works ongoing
| Legs Lane (Off Seaview) | 21668827.56 | Pavement works ongoing
| Willow Lane (Flower Hill ) | 10000000 | To be included in subsequent work order
| Baldwin Crescent | 12500000 | To be included in subsequent work order
| Texas Hill | 15000000 | Scheduled to commence in May
| Churchill Lane | 35000000 | Drainage work ongoing
| Headly Drive | 10000000 | Scheduled to commence in May
| Brown Drive | 25000000 | Scheduled to commence in June
| Simmonds Drive (Montego Hills) | 35000000 | Drainage work ongoing
| Halls Lane (Slat Spring) | 30000000 | To be included in subsequent work order
| Charles Drive | 15000000 | Scheduled to commence in May
| Tower Hill Community Road | 35000000 | To be included in subsequent work order
| Moy Hall community Road | 71615671.36 | Pavement works ongoing
| Meadowvale Community Road | 35000000 | Scheduled to commence in May
| Ebony Drive through to Mud Valley Gutters | 26344603.31 | Drainage works ongoing
| Riverside Drive, Phase 2, Retirement | 37950973.58 | Pavement works ongoing
| Barnett Oval Community Road | 25000000 | Scheduled to commence in May
| Jarrett Terrace community Road | 35000000 | Scheduled to commence in May
Trelawny | Church Street- Gravel Hill, Duanvale | 31204538.45 | Pavement works ongoing
| Samuel Prospect | 35216164.48 | Drainage works ongoing
| Friendship to Wakefield Main Road | 292230566.91 | Scheduled to commence in March
| Smith Hill | 22371828.04 | Scheduled to commence in March
| Hoddington to Kingloss | 25000000 | Scheduled to commence in April
| Penn Road to Stettin | 58356341.07 | Drainage works ongoing
| Butt Up Town Road | 20000000 | Scheduled to commence in April
| Albert Town Road - Grant's Hardware to Butt Up Town Road | 35000000 | Scheduled to commence in April
| Bottom Warsop - Lodge Road | 45000000 | Scheduled to commence in April
| Wirefence to Penn Road (Grandison Town Road) | 23953585.6 | Scheduled to commence in April
| Brampton | 30000000 | Scheduled to commence in April
St. Ann St. Ann | Hammerton to Green Hill | 106305268.79 | Pavement works ongoing
| Peatshop to Ressetta | 40312965.04 | Pavement works ongoing
| Clarksonville to Cedar Valley | 42449093.01 | Pavement works ongoing
| Hessen Castle to Calderwood | 94000000 | To be included in subsequent work order
| Hampton | 84307038.65 | Pipeline works ongoing
| Ricketts Drive to Cardiff All | 25000000 | To be included in subsequent work order
| R/bay School Road | 45000000 | Scheduled to commence in March
| Up Hill, Dumbarton | 35000000 | Scheduled to commence in March
| Top Road to Liberty Valley | 32500000 | Scheduled to commence in March
| Addison Park to Kensington | 45914964.95 | Pavement works ongoing
| Seacrest, Discovery Bay | 50000000 | Scheduled to commence in April
| New Hall to York to Bensonton Cross Roads | 170500000 | Scheduled to commence in April
| Bottom Road to Johnny Spring | 63141100.36 | Scheduled to commence in March
| Cottage to Woodfield | 65957367.21 | Pavement works ongoing
| Paradise Street | 45901702.46 | Pavement works ongoing
| St. Ann's Bay to Lime Hall Square | 90000000 | Scheduled to commence in March
| Steer Town Road | 85000000 | Scheduled to commence in April
St. Mary | Kilancholly | 57538787.45 | Pipeline works ongoing
| Tremolesworth | 48125788.85 | Pipeline works ongoing
| Hibiscus Avenue, Highgate | 27500000 | Scheduled to commence in March
| Friendship to Joe River | 120000000 | Scheduled to commence in March
| Belfield Pen Road | 24392643.75 | Scheduled to commence in April
| Camberwell Main Road | 60547579.47 | Pavement works ongoing
| Gibbs Hill Road | 60000000 | Scheduled to commence in March
| Clarke Road | 50000000 | Scheduled to commence in May
| Brenaird Main Road | 80000000 | Scheduled to commence in March
| Valley Bush to Prospect | 60000000 | Scheduled to commence in March
| Jacks River to Eden Hilll | 48766665.19 | Pavement works ongoing
| Pembroke Hall to Carron Hall | 45000000 | Scheduled to commence in March
| Hunts Town to Crescent | 80000000 | Scheduled to commence in March
| Oracabessa to Hamiton Mountain | 75000000 | Scheduled to commence in May
Portland | Black Hill-Rodney Hall-White Gate | 63274657.74 | Drainage works ongoing
| Canewood Road | 46271045.27 | Base works ongoing
| Commodore | 40000000 | Scheduled to commence in March
| Blueberry - Horsepond - Kildare | 50000000 | Scheduled to commence in April
| Bellevue Road | 24516681.52 | Pavement works ongoing
| Ghost Town Road Anchovy | 35000000 | Scheduled to commence in March
| Islington Road | 38815998.26 | Pavement works ongoing
| Penn Road | 60000000 | Scheduled to commence in March
| Compund Road | 50000000 | Scheduled to commence in May
| Barracks Manchioneal | 40000000 | Scheduled to commence in June